LIVECOMMERCE PLATFORM

Product Requirements Document (PRD) + Technical Specification + Sprint Plan

Document purpose Provide a development-ready specification for a live-commerce operations platform targeted at Vietnamese multi-channel shops, especially TikTok/Facebook livestream operations. Align Product Owner, BA, PM, Backend, Frontend, QA, DevOps, and Data teams on scope, business rules, architecture, sprint sequencing, and acceptance criteria. Serve as the baseline document for estimation, sprint planning, implementation, testing, deployment, and future scaling.

| Metadata | Value |
| --- | --- |
| Document code | LC-PRD-SRS-001 |
| Version | 1.0 |
| Prepared for | Internal development team |
| Prepared by | OpenAI - structured from solution direction approved by project owner |
| Product type | B2B SaaS / Live-commerce operations platform |
| Primary stack | ASP.NET Core + PostgreSQL + Redis + RabbitMQ + SignalR + React |
| Date | 2026-03-12 |

Confidential - internal planning and development use only

# 1. Executive summary

LiveCommerce is a web-based operations platform for livestream and social-commerce sales teams. The system focuses on realtime comment intake, team-based comment assignment, rapid order creation, customer history/risk visibility, live session analytics, and scalable operations for shops processing high order volumes and concurrent users.

The platform is intentionally not positioned as a full ERP or generic POS. Its core business value is to help livestream-heavy sellers reduce missed leads, speed up order confirmation, lower duplicate orders and COD failures, and give owners immediate visibility into live-session performance.

Core value proposition Do not miss customers during livestream or social selling spikes. Create and confirm orders faster from comments and inbox sources. Give managers control over team assignment, conversion rate, and risky customers. Support growth from MVP stage to high-volume operations using event-driven and realtime architecture.

# 2. Product vision, goals, and success metrics

## 2.1 Product vision

Build the leading operational cockpit for livestream and social-commerce teams in Vietnam, starting with TikTok/Facebook-heavy sellers and expanding into a multi-channel live-commerce platform.

## 2.2 Business goals

Reduce missed comments and missed leads during peak live sessions.

Increase order conversion speed and operational consistency across sales teams.

Reduce COD failures, duplicate orders, and manual coordination overhead.

Provide a scalable SaaS foundation that supports thousands of orders per day per merchant.

Create a product architecture that is maintainable, observable, and extensible for later AI and analytics modules.

## 2.3 Product success KPIs

| KPI | Definition | Target / Notes |
| --- | --- | --- |
| Missed comment rate | Unprocessed comments vs. total valid comments in a live session | < 3% after stabilization |
| First response time | Time from comment ingestion to assignment or first processing action | < 30 seconds in normal load |
| Order creation speed | Time for sales user to create order from selected comment | < 15 seconds average |
| Duplicate order rate | Orders unintentionally duplicated for same customer/comment/live session | < 0.5% |
| System availability | Availability of production application and critical services | >= 99.5% MVP, higher later |
| Realtime update latency | Comment/order state reflected to active users | Near realtime, usually within 1-3 seconds |
| Operational scalability | Concurrent users and daily order volume supported | Hundreds of concurrent users, tens of thousands of orders/day |

# 3. Target users and user personas

| Persona | Responsibilities | Main pain points | Main modules used |
| --- | --- | --- | --- |
| Shop Owner | Track sales performance, oversee operations, review risky orders, manage plans and users | No realtime visibility, cannot tell which live session or seller performs best | Dashboard, Orders, Customers, Settings |
| Operation Manager | Assign comments, monitor queues, supervise team, handle escalations | Overloaded queues, duplicate handling, no team-wide visibility | Comment Center, Dashboard, Orders, Follow-up |
| Sales / Chot Don | Receive comments, contact customer, create order, update status | Comment flood, repetitive data entry, no fast customer history | Comment Center, Quick Order, Customer panel |
| Customer Care | Follow up pending customers, confirm orders, maintain customer notes | Scattered information and missing follow-up schedule | Customers, Follow-up, Orders |
| Admin / IT | Manage system settings, product data, access, channel connection health | Complex setup and unstable integrations | Settings, Product, User/Role, Channel connection |

# 4. Scope management

## 4.1 In-scope for initial product line

Multi-user web application for live-commerce team operations.

Realtime comment intake, display, assignment, and processing status.

Quick order creation from comment/customer context.

Customer profile, history, risk/blacklist visibility, and basic tagging.

Live session management and dashboard summary.

Order workflow and order status history.

Role-based access control and configurable operational setup.

Event-driven backend architecture using RabbitMQ and realtime updates via SignalR.

Scalable data design using PostgreSQL, Redis caching, and modular backend services.

## 4.2 Out of scope for MVP

Full accounting and tax system.

Deep warehouse management, purchase management, and advanced inventory planning.

Native mobile apps for Android/iOS (responsive web only at first).

AI recommendation, auto-response, and prediction engines in phase 1.

Deep logistics integrations with all carriers from day one.

Full CRM campaign automation and complex loyalty program.

# 5. Functional module overview

| Module | Purpose | Priority |
| --- | --- | --- |
| Authentication & Authorization | Secure login, shop context, RBAC, permission control | Must have |
| Channel Connection | Manage external channel identity/configuration and ingestion settings | High |
| Live Session Management | Open/close sessions and link comments/orders to the session context | Must have |
| Comment Center | Realtime comment queue, assignment, processing, and audit log | Must have |
| Quick Order | Fast order entry using customer and product context | Must have |
| Customer Management | Profile, history, tags, notes, risk view, follow-up basis | Must have |
| Order Management | Lifecycle of order, status changes, logs, merge/duplicate support later | Must have |
| Risk & Blacklist | Identify risky customers/orders and support manual blacklist | High |
| Dashboard & Analytics | Operational and live performance summary | High |
| Product Management | Master data of product and variants used for order entry | Must have |
| Follow-up | Planned callbacks/messages for not-yet-converted leads | Medium |
| System Administration | Users, roles, templates, settings, retention, audit basics | Must have |

# 6. Detailed business requirements by module

## 6.1 Authentication & Authorization

System shall support login by shop code + username + password.

System shall issue JWT access token and refresh token.

System shall load role and permissions after login.

Unauthorized API access must be blocked.

Sensitive actions must be permission-controlled, not UI-hidden only.

Multi-tenant separation by ShopId is mandatory at data access level.

## 6.2 Channel Connection

Admin can create, edit, activate, deactivate channel connections.

Each connection stores channel type, channel name, external page/account identifier, token/configuration, and status.

System must support validation of connection health and token expiry state.

Webhook or ingestion endpoint must map incoming payloads to the correct shop and channel connection.

## 6.3 Live Session Management

Manager can open a live session with name, channel, start time, and optional external live ID.

Manager can close a live session manually or automatically after configured timeout.

Comments and orders should be linked to a live session when possible.

Live session summary metrics must be available during and after session end.

## 6.4 Comment Center

Comments must appear in near realtime in the correct shop/live session queue.

Each comment has statuses: New, Assigned, InProgress, Ordered, NeedFollowUp, Ignored, Cancelled.

Users can take a comment, assign to another user, update status, mark spam, or mark follow-up.

Comment audit log shall capture status transitions and actor.

Selected comment panel must show customer context, history, risk, notes, and quick order tools.

System must prevent two users from unknowingly processing the same lead without warning.

## 6.5 Quick Order

Sales user can create order directly from selected comment or customer panel.

System shall prefill receiver information if customer has prior data.

System shall calculate subtotal, shipping fee, discount, and final amount.

System shall store order items, assigned user, source comment, and session context.

Order creation shall update comment status to Ordered when successful.

Duplicate/risk warnings should appear before save when matching history is found.

## 6.6 Customer Management

Customer profile stores name, phone, address, notes, risk level, tags, history counters, and channel-linked identifiers.

Users can search by phone, name, and tag.

Customer detail shall show previous orders, risky incidents, and recent comments.

System shall support customer tags such as VIP, New, Repeat Buyer, COD Risk, Follow-up Needed.

System shall update total orders, total spent, and last order date after valid order changes.

## 6.7 Order Management

Orders have statuses such as Draft, PendingConfirm, Confirmed, Packed, Shipping, Delivered, Cancelled, Returned, CODFailed.

Each status change shall be logged.

Users can view, edit, filter, and change status based on permission.

Manager can review risky orders quickly.

Search shall support order no, phone, customer, date range, status, assigned user, and live session.

## 6.8 Risk & Blacklist

System shall maintain manual blacklist records by phone/address/name and level.

System shall warn when receiver phone or customer history indicates repeated COD failure or cancellation pattern.

Risk level must be visible in customer panel and order details.

Risk rules must be configurable in later phase; MVP can start with rule-based thresholds.

## 6.9 Dashboard & Analytics

Dashboard shall show live session volume, queue breakdown, order count, estimated revenue, user performance, and top products.

Realtime counters should update without full page refresh.

Manager should be able to filter by live session, time range, user, and status.

Heavy dashboard queries must use summary tables or cached data where appropriate.

## 6.10 Product Management

Admin can manage product catalog and variants used by quick order form.

Product data includes code, name, category, base price, variant SKU, color, size, status.

Quick order form should only expose active products/variants by default.

## 6.11 Follow-up

Users can create follow-up tasks from comment or customer.

Follow-up contains target time, assigned user, status, and note.

System should support reminder queue in later phase; MVP can expose follow-up list and statuses.

## 6.12 System Administration

Admin can manage users, roles, permissions, channel settings, tags, templates, and operational master data.

System settings should support retention parameters, token expiry checks, and future environment-based controls.

Auditability must exist for critical actions affecting security or data integrity.

# 7. Core business workflows

## 7.1 Comment ingestion workflow

External platform sends comment event to ingestion endpoint.

API validates channel connection and shop mapping.

API stores raw event or publishes normalized event to RabbitMQ immediately.

Worker consumes queue, resolves customer identity if possible, writes comment record, updates metrics, and pushes SignalR event.

Comment appears in Comment Center in near realtime.

## 7.2 Comment processing workflow

Sales/manager opens Comment Center and selects active live session.

User takes or receives assigned comment.

User views customer history, notes, tags, and risk status.

User changes status to InProgress and contacts customer through external channels.

User either creates order, marks follow-up, ignores spam, or marks cancelled.

## 7.3 Order creation workflow

User opens Quick Order from a selected comment.

System prefills customer details and loads active products/variants.

System warns on blacklist or repeated COD failures.

User saves order; backend stores order and items transactionally.

Order log is created, customer counters update, comment status becomes Ordered, dashboard summary refreshes.

## 7.4 Risk handling workflow

System checks phone/address against blacklist and historic failed deliveries.

Risk level is computed or flagged as rule-based warning.

UI highlights risky customer/order before confirmation.

Manager can override, add note, or blacklist manually.

## 7.5 Live dashboard workflow

Active users subscribe to shop/live session groups in SignalR.

New comments or orders publish incremental updates.

Dashboard refreshes counters/charts from cached or summarized sources.

Managers monitor load, performance, and user conversion in realtime.

# 8. Key business rules

| Area | Rule |
| --- | --- |
| Shop isolation | Every transactional and query operation must enforce ShopId scope. No cross-shop leakage is allowed. |
| Comment assignment | Only one active assignee should own a comment at a time. Reassignment must be logged. |
| Comment status | Only valid status transitions should be accepted by backend logic. |
| Order creation | Order and order items must save in a single transaction. |
| Customer match | Phone number is primary match key when present; external customer ID may also be used when trusted. |
| Risk check | Blacklist or historical COD failure should create visible warning before confirmation. |
| Audit log | Critical state changes in comments and orders must be stored with actor and timestamp. |
| Realtime events | UI updates must be event-driven and incremental, not full-list reload on every event. |

# 9. Non-functional requirements

| Category | Requirement |
| --- | --- |
| Performance | Comment intake endpoint must return quickly; heavy processing is asynchronous through RabbitMQ workers. |
| Scalability | System must support hundreds of concurrent users, hundreds of thousands of comments per month, and tens of thousands of orders per day with horizontal scaling strategy. |
| Availability | Critical services should be deployable independently and restart without full-platform outage where possible. |
| Security | JWT auth, RBAC, secure secret management, TLS in production, and strict tenant filtering are mandatory. |
| Observability | Structured logs, request tracing, background job logs, and health checks are required. |
| Maintainability | Solution should follow clean layered architecture and consistent coding standards. |
| Data integrity | Transactional consistency is required for order writes; retries must be idempotent or guarded. |
| Usability | Comment Center and Quick Order must be optimized for speed and low-click operation. |
| Deployment | Solution must run in Dockerized Linux environment with clear environment-based configuration. |

# 10. Technical architecture

Recommended architecture: Modular monolith with dedicated worker and realtime components. This keeps development practical while still supporting scale and separation of concerns.

| Component | Technology | Responsibility |
| --- | --- | --- |
| Web API | ASP.NET Core Web API | Business APIs, authentication, configuration, query endpoints |
| Realtime service | ASP.NET Core SignalR | Push comments, statuses, and dashboard updates to connected clients |
| Background worker | ASP.NET Core Worker Service | Consume RabbitMQ queues, aggregate data, apply background rules |
| Frontend | React + Vite | Operational web interface for all user roles |
| Database | PostgreSQL | Primary relational store for transactional data and summarized data |
| Cache | Redis | Distributed cache, idempotency support, optional SignalR Redis backplane |
| Message broker | RabbitMQ | Asynchronous event pipeline and workload decoupling |
| Reverse proxy | Nginx | TLS termination and routing to app containers |
| Containerization | Docker / Docker Compose initially | Consistent environment for local and production deployment |

Architecture principles Keep write-paths transactionally correct and read-paths optimized via summaries/caching. Move bursty or expensive workflows out of synchronous HTTP requests. Design every major component to be horizontally scalable later. Do not start with microservices for every module; separate only the parts that justify operational independence.

# 11. Backend development specification

## 11.1 Recommended solution structure

LiveCommerce.Api - controllers, auth, OpenAPI, HTTP pipeline.

LiveCommerce.Application - use cases, DTOs, interfaces, validators.

LiveCommerce.Domain - entities, enums, constants, domain rules.

LiveCommerce.Infrastructure - persistence, repositories, message integrations, Redis, background adapters.

LiveCommerce.SignalR - hubs and push services.

LiveCommerce.Worker - queue consumers and aggregators.

LiveCommerce.Shared - shared contracts, common utilities, cross-cutting helpers.

## 11.2 API design standards

Use RESTful endpoints under /api/v1.

All write APIs must validate tenant scope and permission.

Use consistent response envelopes for paging and error handling.

Use OpenAPI/Swagger for internal dev documentation.

Implement health endpoints for API, DB, RabbitMQ, Redis.

## 11.3 Backend coding standards

Use async/await for I/O bound operations.

Separate command/write and query/read logic when complexity grows.

Use EF Core for common CRUD and Dapper for heavy dashboard queries if necessary.

Use FluentValidation for request validation.

Use structured logging via Serilog or equivalent.

Guard critical workflows with database transaction boundaries.

## 11.4 Realtime design

Use SignalR hub groups by shop, live session, and possibly user.

Push incremental delta events only, not entire datasets.

Use Redis backplane once more than one app instance is deployed.

## 11.5 Queue/event design

Use RabbitMQ queues for comment ingress, order-created events, risk-check tasks, and dashboard aggregation triggers.

Implement retry/dead-letter strategy for failed message processing.

Design consumers to be idempotent when possible.

# 12. Frontend development specification

Frontend is a responsive, operational web application designed for speed, visibility, and low-friction repetitive work. Primary users operate on desktop/laptop screens, but layouts should remain usable on smaller widths where practical.

## 12.1 Recommended stack

React + Vite for app foundation.

TypeScript strongly recommended for maintainability.

Ant Design or MUI for mature component library; keep component usage consistent.

SignalR JavaScript client for realtime subscriptions.

Axios or equivalent for HTTP client layer.

State management via Zustand or Redux Toolkit depending on team preference.

## 12.2 Frontend architecture principles

Separate pages, business components, shared UI components, API clients, state, and utility modules.

Keep Comment Center highly optimized for keyboard/mouse speed.

Persist selected filters and session context where helpful.

UI must clearly expose risk state, current assignee, and processing status.

Do not tightly couple components to raw backend payload shape; use typed view models/adapters.

## 12.3 Primary screens

Login

Dashboard

Comment Center

Order List / Detail

Customer List / Detail

Product Maintenance

Settings / User / Role / Channel

Follow-up list

# 13. Database specification

PostgreSQL is the primary transactional store. The schema must be multi-tenant aware and optimized for write-heavy, time-based datasets such as comments, orders, and logs.

| Data domain | Main tables |
| --- | --- |
| Identity & tenant | shops, users, roles, permissions, role_permissions |
| Channel & live | channel_connections, live_sessions |
| Commerce core | customers, customer_tags, customer_tag_mappings, products, product_variants, orders, order_items |
| Operational queue context | comments, comment_logs, follow_ups, blacklists |
| Analytics / summaries | live_session_summaries, daily_shop_stats, user_live_stats, product_live_stats (recommended) |

## 13.1 Database design rules

Every transactional table must include ShopId directly or be safely joinable through parent entity.

Use bigint identity or bigserial IDs to avoid future exhaustion.

Timestamp fields should consistently use UTC in backend logic and display local time in UI.

Keep audit/log tables append-only where practical.

## 13.2 Indexing strategy

Index comments by shop_id + live_session_id + status + comment_time desc.

Index comments by assigned_user_id + status when queue ownership is frequently filtered.

Index orders by shop_id + status + created_date desc.

Index customer phone and external customer identifier.

Do not over-index high-write tables; base indexes on real query patterns.

## 13.3 Partitioning guidance

Prepare comments and logs for partitioning by month once volumes justify it.

Prepare orders for time-based partitioning if daily volume grows substantially.

Use summary tables for dashboard-heavy analytics rather than scanning large raw tables repeatedly.

## 13.4 Data retention and archival

Define retention strategy for raw event payloads and large logs.

Keep transactional history long enough for business traceability.

Archive or compress low-value raw payload data if storage cost becomes material.

# 14. Security, DevOps, and operations

| Area | Requirement / Direction |
| --- | --- |
| Authentication | JWT access token + refresh token |
| Authorization | RBAC with backend-enforced permissions |
| Secrets | Use environment variables or secret manager; never hardcode tokens/credentials |
| Transport security | Use HTTPS/TLS in production |
| Logging | Structured logs with correlation ID / request ID |
| Monitoring | Health checks, container health, queue depth visibility, error alerting |
| Backup | Routine PostgreSQL backup and restoration test |
| Deployment | Dockerized services on Ubuntu Linux, reverse-proxied by Nginx |
| Scalability | Support horizontal app scaling; add Redis backplane for SignalR when multi-instance |
| Recovery | Worker retry and dead-letter queue for failed events |

# 15. High-level API groups

| API group | Examples of endpoints |
| --- | --- |
| Auth | POST /auth/login, POST /auth/refresh, GET /auth/me |
| Users / Roles | GET /users, POST /users, GET /roles, PUT /roles/{id}/permissions |
| Live sessions | GET /live-sessions, POST /live-sessions, POST /live-sessions/{id}/close |
| Comments | GET /comments, POST /comments/webhook, POST /comments/{id}/assign, POST /comments/{id}/status |
| Customers | GET /customers, GET /customers/{id}, POST /customers/{id}/tags |
| Orders | GET /orders, POST /orders, POST /orders/{id}/status |
| Blacklists | GET /blacklists, POST /blacklists |
| Follow-up | GET /follow-ups, POST /follow-ups, POST /follow-ups/{id}/done |
| Dashboard | GET /dashboard/live-summary, GET /dashboard/user-performance, GET /dashboard/top-products |

# 16. Sprint plan and delivery roadmap

Suggested sprint length: 2 weeks. The plan below assumes one product squad with BA/PM + Backend + Frontend + QA + DevOps support. Team size and business urgency may adjust sprint packing.

| Sprint | Objective | Main output |
| --- | --- | --- |
| Sprint 0 | Foundation and planning | Project setup, environments, coding standards, baseline architecture, backlog refinement |
| Sprint 1 | Identity and shell | Auth, RBAC basics, React shell, PostgreSQL baseline, CI/CD skeleton |
| Sprint 2 | Comment intake v1 | Webhook ingestion, RabbitMQ flow, comment storage, basic Comment Center list |
| Sprint 3 | Realtime operations | SignalR push, assignment workflow, selected comment panel, customer quick lookup |
| Sprint 4 | Quick order v1 | Order create/edit, products/variants, customer linkage, order logs |
| Sprint 5 | Dashboard and risk v1 | Live summary, user performance, blacklist warnings, summary worker |
| Sprint 6 | Admin and hardening | Settings, channels, users/roles polish, follow-up basics, audit completeness |
| Sprint 7 | Performance, QA, release prep | Load test fixes, production readiness, backup/monitoring, UAT, release candidate |

## Sprint 0 - Foundation and planning

Finalize backlog and acceptance criteria.

Create repositories, branching strategy, code style rules, environment matrix.

Prepare Docker local stack for PostgreSQL, Redis, RabbitMQ.

Establish architecture skeleton and solution structure.

Deliverables: approved technical baseline, dev environment guide, initial CI pipeline.

## Sprint 1 - Identity and shell

Implement authentication, token flow, role and permission framework.

Create React app shell, layout, route guards, login page.

Create initial DB migrations for tenant, user, role tables.

Deliverables: login working end-to-end, secured sample pages, tenant-aware foundation.

## Sprint 2 - Comment intake v1

Build channel connection entities and webhook endpoint.

Publish incoming events to RabbitMQ.

Create worker consumer to persist normalized comments.

Create Comment list page with filters and pagination.

Deliverables: comments arriving from integration test source into UI-backed database.

## Sprint 3 - Realtime operations

Add SignalR hub and client subscriptions.

Implement comment take/assign/update-status flows.

Build selected comment panel with customer summary.

Deliverables: realtime queue operations usable by sales/manager roles.

## Sprint 4 - Quick order v1

Build product and variant APIs and maintenance pages.

Implement quick order form, order save transaction, order list/detail.

Update customer counters and comment->order status linkage.

Deliverables: full comment-to-order basic workflow.

## Sprint 5 - Dashboard and risk v1

Build blacklist records and backend risk checks.

Implement summary tables/queries and dashboard widgets.

Show user performance and top products per live session.

Deliverables: owner/manager visibility and risk warnings.

## Sprint 6 - Admin and hardening

Finalize user/role UI, tags, templates, and settings.

Add follow-up module basics.

Improve validation, error messages, and audit completeness.

Deliverables: admin readiness for pilot merchant onboarding.

## Sprint 7 - Performance, QA, release prep

Load and concurrency testing for comments, orders, and realtime.

Tune indexes, cache, worker scaling, and queue behavior.

Prepare backup scripts, monitoring, alerting, and rollback plan.

Deliverables: release candidate and production checklist completed.

# 17. Testing strategy and acceptance

## 17.1 Test types

Unit tests for core business services and validators.

Integration tests for API + database + queue workflows.

UI tests for core paths such as login, comment handling, and order creation.

Load tests for comment bursts, concurrent users, and dashboard refresh scenarios.

UAT with realistic live-session data before production release.

## 17.2 Minimum acceptance criteria for MVP release

User can log in, access permitted modules only, and operate within shop scope.

Comment events can be ingested, displayed, assigned, and status-updated reliably.

Sales can create order from customer/comment context without data corruption.

Managers can view live session summary and user performance basics.

Blacklist/risk warnings are visible on relevant customers/orders.

System runs in Dockerized environment with documented deployment steps.

# 18. Suggested delivery responsibilities by role

| Role | Main responsibility |
| --- | --- |
| Product Owner / Business Owner | Prioritize scope, confirm business rules, approve UAT |
| BA / PM | Refine requirements, maintain backlog, coordinate dependencies, track acceptance |
| Backend Developer | API, worker, queue, business rules, persistence, security |
| Frontend Developer | React UI, operational flows, realtime client, UX performance |
| QA Engineer | Test plan, regression, scenario validation, UAT support |
| DevOps / Infra | Environment, Docker, deployment, monitoring, backup, security setup |
| Data / Analytics (later) | Advanced reporting, retention, future AI/reporting enablement |

# 19. Key delivery risks and mitigations

| Risk | Potential impact | Mitigation |
| --- | --- | --- |
| External channel API instability | Comment ingestion breaks or becomes inconsistent | Decouple ingestion via queue, store raw payload, build retry/monitoring |
| Concurrent processing conflicts | Duplicate orders or user confusion | Use assignment locking patterns, backend validation, clear UI states |
| Dashboard on raw large tables | Slow UI and DB overload | Use summary tables, cache, and tuned indexes |
| Over-scoping MVP | Delayed release and unstable product | Keep MVP scope strict and postpone non-core modules |
| Insufficient observability | Slow incident resolution | Adopt structured logging, queue metrics, health checks from early sprints |
| Poor tenant isolation | Critical data leakage risk | Enforce ShopId in every layer and test isolation explicitly |

# 20. Post-MVP roadmap suggestions

Deep TikTok/Facebook platform integration and reliability improvements.

AI-assisted response suggestions and hot-lead scoring.

Advanced duplicate detection and order merge recommendations.

Carrier integrations and logistics status sync.

Warehouse handoff and packed/shipping workflow enhancement.

Financial reconciliation dashboard.

Data warehouse / BI export for advanced analytics.

# Appendix A - Recommended environment matrix

| Environment | Purpose | Notes |
| --- | --- | --- |
| Local | Developer machine | Docker Compose with API, worker, PostgreSQL, Redis, RabbitMQ, frontend |
| DEV | Shared integration | Used for sprint integration and smoke testing |
| UAT | Business validation | Close to production config with anonymized or controlled data |
| PROD | Live operation | TLS, monitoring, backups, restricted access, scaling controls |

# Appendix B - Recommended package/library direction

| Layer | Suggested libraries / tools |
| --- | --- |
| ASP.NET Core | JWT Bearer auth, OpenAPI/Swagger, HealthChecks, Serilog |
| Data | Npgsql, EF Core, optionally Dapper for heavy reads |
| Validation | FluentValidation |
| Messaging | RabbitMQ.Client or MassTransit |
| Cache / realtime support | StackExchange.Redis |
| React | Vite, TypeScript, Axios, SignalR JS client, Ant Design or MUI |
| DevOps | Docker, Docker Compose, Nginx, CI/CD pipeline tooling |

# Appendix C - Development start order

Project setup and environment provisioning.

Authentication / authorization baseline.

Comment ingestion and storage.

Comment Center and realtime updates.

Customer panel and Quick Order.

Dashboard and risk module.

Admin/setup pages and hardening.

Load testing and release readiness.

Document usage note This document is intended to be used as the primary handoff package to development and QA for initial planning and implementation. Before each sprint starts, BA/PM should refine the selected stories into story-level acceptance criteria and UI/API task breakdown. Any integration-specific behavior for TikTok/Facebook/Zalo should be captured in separate integration notes once connector details are confirmed.